## Sheet1
Sprint 1
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05 | 2023-03-06
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Decide the frontend designs | Decide on wireframes and ways to track the progress, scrum board | Pavan Sai, Pavan Satyam | 8 | 2023-02-21: 2; 2023-02-23: 1; 2023-02-25: 1; 2023-03-02: 2; 2023-03-04: 2
Backend Technology Search | Deciding on backend Technology and design | Pavan Sai, Alekhya | 8 | 2023-02-22: 1; 2023-02-23: 1; 2023-02-25: 1; 2023-02-27: 2; 2023-03-01: 1; 2023-03-02: 1; 2023-03-05: 2
Front End Technology Search | Deciding on front end technology and design | Pavan Sai, Alekhya | 8 | 2023-02-21: 1; 2023-02-22: 1; 2023-02-23: 2; 2023-02-25: 1; 2023-02-28: 1; 2023-03-02: 1; 2023-03-04: 2
Sprint Details and Task allocation | What all details are required to be documented, scrum board | Pavan Sai, Piyush, Pavan Satyam | 8 | bar: 2023-02-22 to 2023-02-24; 2023-02-26; 2023-03-02; 2023-03-06
Architecture and UML Diagram | What should be the Architecture of the Project | Pavan Sai, Pavan Satyam, Alekhya | 8 | 2023-02-23: 1; 2023-02-24: 1; 2023-02-25: 1; 2023-02-27: 2; 2023-03-01: 1; 2023-03-02: 1; 2023-03-03: 1
p
Remaining Effort |  |  | 40 | 37 | 34 | 28 | 26 | 22 | 21 | 17 | 16 | 14 | 8 | 7 | 3 | 1 | 0
Ideal Trend |  |  | 40 | 37.1429 | 34.2857 | 31.4286 | 28.5714 | 25.7143 | 22.8571 | 20 | 17.1429 | 14.2857 | 11.4286 | 8.5714 | 5.7143 | 2.8571 | 0
Sprint 2
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Design the routing flow for the users, Landing/Homepage for the user | Create the flow of the website and the Homepage for the user | Pavan Sai, Piyush, Pavan Satyam | 4 | 2023-03-08: 2; 2023-03-10: 1; 2023-03-12: 1
Design Gym Employee Dashboard, with login auth | Creating a dashboard for gym employee for membership claims and hours management | Pavan Sai, Pavan Satyam | 10 | 2023-03-07: 1; 2023-03-08: 1; 2023-03-09: 2; 2023-03-11: 1; 2023-03-13: 1; 2023-03-15: 1; 2023-03-16: 2; 2023-03-18: 1
Design and develop Membership page | Creating a membership status page for user view | Pavan Sai, Alekhya | 11 | 2 | 1 | 1 |  | 1 | 2 |  | 1 | 1 | 1 | 1
Design and develope Gym Employee Dashboard | Creating a dashboard for gym employee to Add or update the hours | Pavan Sai, Alekhya, Pavan Satyam | 10 | 2023-03-08: 1; 2023-03-09: 1; 2023-03-10: 1; 2023-03-11: 1; 2023-03-12: 1; 2023-03-13: 1; 2023-03-15: 1; 2023-03-16: 2
Design Rest APIs | Api for all the services used in above components | Pavan Sai | 11 | bar: 2023-03-07 to 2023-03-17; 2023-03-19
Remaining Effort |  |  | 46 | 42 | 36 | 31 | 28 | 24 | 19 | 16 | 14 | 10 | 4 | 2 | 1 | 0 | 0
Ideal Trend |  |  | 46 | 42.7143 | 39.4286 | 36.1429 | 32.8571 | 29.5714 | 26.2857 | 23 | 19.7143 | 16.4286 | 13.1429 | 9.8571 | 6.5714 | 3.2857 | 0
Sprint 3
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Setup of Project and updating the modules required | Built a Project for Frontend and Bakcend with required modules | Pavan Sai, Pavan Satyam | 14 | 2 | 1 | 1 |  | 1 | 2 | 1 | 1 |  |  | 1 | 1 | 1 | 2
Design and develop Membership page | Creating a membership status page for user view | Pavan Sai, Alekhya | 10 | 2023-03-21: 2; 2023-03-22: 1; 2023-03-23: 1; 2023-03-25: 1; 2023-03-26: 2; 2023-03-27: 1; 2023-03-28: 1; 2023-03-31: 1
Design and develope Member Dashboard | Creating a dashboard for gym employee to Add or update the hours | Alekhya, Pavan Satyam | 12 | 2 | 1 | 1 |  | 1 | 2 | 1 | 1 |  |  | 1 | 1 | 1
Design Rest APIs | Api for all the services used in above components | Pavan Sai | 10 | 2023-03-21: 1; 2023-03-22: 1; 2023-03-23: 1; 2023-03-24: 3; 2023-03-25: 1; 2023-03-27: 1; 2023-03-30: 2
Remaining Effort |  |  | 46 | 39 | 35 | 31 | 28 | 24 | 18 | 14 | 11 | 11 | 9 | 6 | 4 | 2 | 0
Ideal Trend |  |  | 46 | 42.7143 | 39.4286 | 36.1429 | 32.8571 | 29.5714 | 26.2857 | 23 | 19.7143 | 16.4286 | 13.1429 | 9.8571 | 6.5714 | 3.2857 | 0
Sprint 4
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-15 | 2023-04-16 | 2023-04-17
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Deisgn REST APIs for the HCMemeber page | Build all the REST APIs for the HC Member page | Pavan Sai | 15 | 1 |  | 1 | 1 | 1 | 3 | 1 |  | 2 |  | 2 |  | 2 | 1
Design the Frontend Dashboard for HCMember page | Build all the REST APIs and Frontend Components for the HCMember page | Pavan Sai, Pavan Satyam | 12 | 1 | 2 | 1 | 2 | 1 |  | 1 |  | 1 |  | 1 |  | 1 | 1
Design the Analytics board for HCMember page | Build all the Frontend Graphs/Charts for HCMember page | Pavan Sai, Alekhya | 12 | 1 | 1 | 2 | 1 | 2 | 1 |  |  |  | 1 |  |  | 2 | 1
Design the Enroll and Checkin/Checkout functionality for HCMember page | Build the Checkin/Checkout and Enroll functionality for HCMember page | Pavan Sai, Piyush | 10 | bar: 2023-04-04 to 2023-04-06; 2023-04-08 to 2023-04-10; 2023-04-12; 2023-04-14; 2023-04-16 to 2023-04-17
Remaining Effort |  |  | 49 | 45 | 41 | 36 | 32 | 27 | 22 | 19 | 19 | 15 | 14 | 10 | 10 | 4 | 0
Ideal Trend |  |  | 49 | 45.5 | 42 | 38.5 | 35 | 31.5 | 28 | 24.5 | 21 | 17.5 | 14 | 10.5 | 7 | 3.5 | 0
Sprint 5
Backlog Item | Task | Task Owner | Initial Estimate (in hours) | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-21 | 2023-04-22 | 2023-04-23 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-04-30 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19
Error handling for login and redirection for search | Error handling, css clean up, home page redirection for search, and api changes | Pavan Sai | 14 | 2023-04-20: 4; 2023-04-21: 2; 2023-04-27: 4; 2023-04-29: 4
fixes to HCM contoller, login controller components | making changes to api controllers | Pavan Sai, Pavan Satyam | 12 | 2023-04-19: 1; 2023-04-21: 1; 2023-04-22: 3; 2023-04-25: 4; 2023-04-30: 1; 2023-05-01: 2
dashboard, homepage and Enroll pages components | changes to css and api integration | Pavan Sai, Alekhya | 10 | 2023-04-18: 4; 2023-04-19: 1; 2023-04-20: 1; 2023-04-21: 4
Non Member type and Member type access handlers and api for the same | updating the userroles and handling access within the APIs | Pavan Sai, Piyush | 15 | 2023-04-24: 5; 2023-04-26: 5; 2023-04-30: 1; 2023-05-01: 2; 2023-05-02: 1; 2023-05-04: 1
Deploy to AWS | Deploying the code to AWS with load balancing | Team | 5 | 2023-05-04: 1; 2023-05-05: 4
Remaining Effort |  |  | 56 | 52 | 50 | 45 | 42 | 38 | 35 | 35 | 30 | 26 | 21 | 17 | 17 | 13 | 11 | 7 | 6 | 6 | 4 | 0
Ideal Trend |  |  | 56 | 53.0526 | 50.1053 | 47.1579 | 44.2105 | 41.2632 | 38.3158 | 35.3684 | 32.4211 | 29.4737 | 26.5263 | 23.5789 | 20.6316 | 17.6842 | 14.7368 | 11.7895 | 8.8421 | 5.8947 | 2.9474 | 0